NeatThread Platform

1. Project Planning & Management

Project Title:

NeatThread

Objective:

The objective of the NeatThread project is to develop a secure, user-friendly, and scalable web-based e-commerce platform for clothing using ASP.NET Core. The system aims to provide customers with a seamless shopping experience by enabling easy browsing, searching, and filtering of products, along with secure user authentication, shopping cart management, and smooth checkout with integrated online payment. Additionally, the platform seeks to support administrators through an efficient dashboard for managing products, categories, and orders. The project also focuses on applying N-Tier Architecture and best practices to ensure maintainability, performance, and scalability.

Problem Statement:

Many online clothing stores have complex interfaces, limited product organization, and inefficient management systems for administrators. Customers often struggle to easily browse products, compare items, and complete purchases smoothly, while store owners need a better way to manage products, categories, and orders efficiently.

Scope:

- Product catalogue with categories, search, and filters

- Session-based (or state-managed) shopping cart

- Stripe payment gateway integration

- ASP.NET Identity authentication and role management

- Admin panel for product, category, and order management

- Front-end developed using React with a responsive UI styled by Tailwind CSS

- Deployment to Microsoft Azure

Out of Scope:

- Mobile application

- Multi-vendor marketplace

- Loyalty or rewards programme

Technologies:

ASP.NET Core MVC 8 (Web API), Entity Framework Core, SQL Server, ASP.NET Identity, Stripe.net, React.js, Tailwind CSS, Axios, React Router, Microsoft Azure

Project Plan:

| Phase | Task | Start | End | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Project setup (API + React + Tailwind) | May 1 | May 3 | Dev Team | Planned |
| Week 1 | Database design (ERD + schema) | May 2 | May 5 | Backend Dev | Planned |
| Week 1 | Authentication (Identity + JWT | May 4 | May 7 | Backend Dev | Planned |
| Week 1 | Frontend base structure (React routing + layout) | May 5 | May 8 | Frontend Dev | Planned |
| Week 2 | Product module (CRUD + categories API) | May 9 | May 12 | Backend Dev | Planned |
| Week 2 | Product listing + search + filters (UI + API) | May 10 | May 14 | Full Stack | Planned |
| Week 2 | Shopping cart (state management) | May 12 | May 15 | Full Stack | Planned |
| Week 2 | RBAC (Admin / Customer roles) | May 13 | May 15 | Backend Dev | Planned |
| Week 3 | Admin dashboard (products + categories) | May 16 | May 19 | Full Stack | Planned |
| Week 3 | Order system (checkout + order creation) | May 17 | May 20 | Backend Dev | Planned |
| Week 3 | Stripe payment integration | May 18 | May 21 | Backend Dev | Planned |
| Week 3 | User profile + order history | May 19 | May 22 | Full Stack | Planned |
| Week 4 | UI polishing (React + Tailwind) | May 23 | May 26 | Frontend Dev | Planned |
| Week 4 | Testing & bug fixing | May 25 | May 28 | QA | Planned |
| Week 4 | Deployment (Azure) | May 27 | May 29 | DevOps | Planned |
| Week 4 | Final documentation | May 29 | May 31 | All | Planned |

Task Assignment & Roles:

| Role | Team Member | Responsibilities |
| --- | --- | --- |
| Team Leader / Full Stack Developer | Ahmed Tarek | Project planning, task distribution, progress tracking, contributes to front-end, back-end, and database development |
| Full Stack Developer | Karim Salama | Develops front-end (React + Tailwind) and back-end APIs, participates in database design and testing |
| Full Stack Developer | Ziad Mohamed | Works on UI components, API integration, and contributes to database and business logic implementation |
| Full Stack Developer | Eslam Mohamady | Implements features across front-end and back-end, participates in debugging and system integration |
| Full Stack Developer | Ziad Eid | Develops application features, collaborates on admin panel and API development, assists in testing |
| Full Stack Developer | Mohamed Ashraf | Contributes to front-end and back-end development, deployment, and documentation |

Risk Assessment & Mitigation Plan:

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| JWT token security issues | Medium | High | Store tokens securely, use HTTPS, set proper expiration and refresh tokens |
| API integration issues (React ↔ ASP.NET) | Medium | High | Use consistent API contracts, test endpoints with Postman before integration |
| Stripe payment integration errors | Medium | High | Use Stripe sandbox for testing, handle errors and allow retry mechanism |
| Database migration conflicts | Medium | Medium | Use feature branches and assign one developer to manage migrations |
| State management bugs (cart issues) | Medium | Medium | Use reliable state management (Context/Redux) and test cart scenarios thoroughly |
| Unauthorized access (RBAC issues) | Low | High | Implement proper role checks and test admin/customer permissions |
| Deployment failure on Azure | Low | High | Test deployment locally and on staging before production |
| Performance issues with many users | Low | Medium | Optimize queries, use pagination and caching where needed |
| UI responsiveness issues | Medium | Low | Test on multiple screen sizes and use Tailwind responsive design |
| Data loss or crashes | Low | High | Use backups on Azure and implement proper error handling and logging |

KPIs (Key Performance Indicators):

| KPI | Metric | Target | Measurement Method |
| --- | --- | --- | --- |
| Page Load Time | Home / Product pages | < 2 seconds | Browser DevTools (Lighthouse) |
| API Response Time | All API endpoints | < 300ms | Postman / Integration tests |
| System Uptime | Azure App Service | > 99% | Azure Monitor |
| Successful Checkout Rate | Completed orders / cart sessions | > 85% | Database tracking (orders vs carts) |
| User Registration Rate | New users (first month) | > 30–50 users | ASP.NET Identity user count |
| Bug Rate Post-Testing | Bugs per test cycle | < 3 | Bug tracking log |
| UI Responsiveness | Mobile & desktop screens | 100% responsive | Test on different screen sizes |
| Code Coverage | Unit testing coverage | > 60–70% | Visual Studio Test Explorer |
| Error Rate | Failed API requests | < 5% | Logging system / middleware logs |